## IntroBest Practices
Optimizing Relationships Between Marketing & IT
Friction has transpired in the relationship between Information Technology (IT) and commercial business units globally due to the complexity of marketing delivery and technology available in the marketplace and the process of introducing new technology into a company’s ecosystem. This breakdown of communication is causing reduced performance visibility and an inability to execute commercial strategies, preventing many companies from expanding their presence across digital channels that are highly successful in other industries.
This workbook is your guide to assuring accountability for a successful installation and/or upgrade within your marketecture stack. Each tab provides direction and suggestions for ownership/responsibility with implementation. It is best to go throught the tabs in order where you'll find instructions and guiding comments by hovering over certain areas within the workbook.
Best Practices
By utilizing these best practices, organizations can navigate through their IT departments to advance business goals through digital transformation. This optimization will drive businesses forward in one or more of the following areas:
• Revenue Recognition • Savings • Efficiency/Automation • Self-service • Guest Satisfaction | • Data Accuracy • Compliance • Preventative Maintenance • Reductions of Defects
These best practices will enable companies to:
• Identify relationships and dependencies between systems and services
• Identify gaps and strengthen relationships between stakeholders through the adoption of these best practices
• Establish responsibilities in a multi-stakeholder and accountability environment
• Utilize a project management framework guide for new technology implementations and/or system upgrades
What needs to be done BEFORE a contract is signed?
• Complete discovery process to confirm the need and identify the degree of operational suitability
• Identify if existing systems already include a component to solve this issue
• Determine the cost-benefit
• Create an implementation plan and identify the right resources
• Align on expectations
• Confirm integration/connectivity ability with all systems a new process will influence or leverage
• Identify impact to others/systems/constraints/dependencies
Getting Started - Communication and the inclusion of both teams are crucial at the beginning of the project
• Get the right departments/people involved by identifying and including all those affected right from the start
• Document assumptions
• Utilize the Marketecture template to document all systems that touch marketing
• Define scope to avoid scope creep and create multiple phases if necessary
• Ensure a well-defined plan is documented with precise deadlines and deliverables
Utilize the Project Management Framework - Taking the time upfront to plan will save time throughout the project
• Requirements
• Stakeholders
• Project Plan
• Testing
• In Scope vs. Out of Scope

## Marketecture Diagram
This illustration is meant to help plan roadmaps, with each block representing a new launch and/or upgrade. Marketecture diagrams make it easier for an audience to understand how products and services work together. Select which products/features you currently have and their current ownership; this would be the foundation of your marketecture plan. You can select which elements you'd like to add or upgrade and use this workbook to guide you through its installation.

## Glossary
Hospitality Marketecture Diagram Glossary
Activation Section | This section addresses all the tools needed to deliver customer content, incorporate feedback, detect patterns and measure engagement
Audiences | Groups of individuals or organizations who could in some way be exposed to your offering, either directly or through your marketing and communications
Banner | Banner advertising refers to the use of a graphic display that stretches across the top, bottom or sides of a website or online media. The horizontal type of banner advertisement is called a leaderboard, while the vertical banners are called skyscrapers and positioned on a web page's sidebars. Banner ads are image-based rather than text-based and are a popular form of online advertising. The purpose of banner advertising is to promote a brand and/or to get visitors from the host website to go to the advertiser's website.
Bed Banks | A bed bank (also called a wholesaler) is a B2B company that purchases rooms from accommodation providers in bulk at a discounted, fixed price for specific dates and sells them to OTAs, travel agents, airlines or tour operators
Call Center | This generally refers to reservations centers, help desks, information lines or customer service centers, regardless of how they are organized or what types of transactions they handle
Chatbot | A computer program designed to simulate human conversation typically powered by rules and artificial intelligence
Consent Management | A system or process allowing customers to determine what personal data they are willing to share with a business
Central Reservation System (CRS) | A reservation management software that allows your hotel to manage inventory and rates in real-time so that your hotel can manage reservations and the related processes more efficiently
Customer Data Platform | The central location for all customer data that provides customer profile unification, data segmentation/profiling, data orchestration and historical transactions
Customer Journey | A comprehensive view of your customer's experience at each stage in the following six categories: 1. Inspiration and Research 2. Booking 3. Pre-Arrival 4. Check-in 5. In-house Experience 6. Check-out and Post-stay
Data Aggregators | Data mining systems that spread business information online then collect and share that business data with many sources, including search engines
Data Lake | A data repository for storing extensive data feeds, both structured and unstructured
Data Management Platform (DMP) | A unifying platform to collect, organize and activate first-, second- and third-party audience data from any source, including online, offline, mobile and beyond
Golden Record | A single, well-defined version of all the data with the organization's CDP entities in an organizational ecosystem, sometimes called the "single version of the truth"
Look-alike | An audience of prospective new customers, generated (often algorithmically) from a “seed audience” of current customers or likely customers
Martech | The combination of marketing techniques and technology to create, communicate, analyze, deliver, test, measure, automate, integrate, adjust and streamline marketing efforts
Metasearch Engine | This is an engine (or search aggregator) that is an online information retrieval tool that uses the data of a web search engine to produce its results. Metasearch engines take input from a user and immediately query search engines for results to gather, rank and present data to users.
Online Travel Agency (OTA) | A web-based marketplace that allows consumers to research and book travel products and services, including hotels, flights, cars, tours, cruises, activities, and more, directly with travel suppliers
Property Management System (PMS) | A software application for the operations of hospitality accommodations
Primary Data | Data that comes directly from your audience which is collected straight from your customers, site visitors, email list subscribers, loyalty members or other people interacting directly with your organization
Processing & Storage Section | This section includes everything needed for data storage, cleansing, analysis and content creation.
Retargeting | Retargeting, also known as remarketing, is a form of online advertising that can help you keep your brand in front of bounced traffic after they leave your website. For most websites, only 2% of web traffic converts on the first visit. Retargeting is a tool designed to help companies reach the 98% of users who don't convert right away.
Revenue Management System (RMS) | A software solution allowing users to carry out important revenue management tasks more efficiently and effectively, using property and market data
Secondary Data | Data information that another company has collected
Unification Section | This section on the diagram includes everything needed to capture and unify customer data.

## Project Planner Directions
Directions Tab
Name | Purpose | Description
Requirements | The requirements tab will help you define, track and prioritize requirements for the scope of the Project and verify requirements are tested or available as a functionality in the 'Test Tracking' tab | This tab highlights each requirement you will install, redesign or build new functionality. It prioritizes functionality into monthly sprints, which are planned into timelines on the 'Project Plan' tab. Its second purpose is to track verification results and record testing activities against Dev, Test and Production.
RACI | The RACI tab is for stakeholder management. From there, you can keep track of Project Names, Roles and Responsibilities, including who's responsible, who needs to approve, who can support, and needs to be kept informed about the project. | This tab highlights roles and responsibilities on the project between the individual team members by project activities. It's helpful to ensure who's accountable for what for collaboratively managing the project.
Project Plan | The customizable project plan tab is for managing project activities, deliverables, timelines and needs of individuals. | This tab highlights weekly project activities associated with delivery for architecture, build, test and deployment. All items in black are the responsibility of (company) to drive along with overall engagement and actions to support build. Items in orange will need Q and A to support.
Test Tracking | The test tracking tab is a quick log to track functional testing results. | This log allows the 'tester' to record the results of items that don't function as expected based on requirements and design discussions. The appropriate role identified will fix the bugs and mark the status of resolution and migration to test.
Action Log | The action log is task-level activities management. | This tab highlights particular tasks needed from team members, with dates, who it's assigned to and when it's required to ensure management of the overall project timelines. It's critical to meet the delivery of action items by the date defined, or the go-live date will be delayed.
Backlog | The backlog is for items out of scope for the current phase of project deliverability which is often considered a parking lot. | This tab will capture items for future phase releases. As we learn about your business and requirements, you will capture these for later discussion around priorities and sprint release post Phase I.
Hints | You may need to duplicate tabs to handle in a single workbook if implementing multiple systems. Consider including a Visio diagram that shows the flow from tab to tab and provides a bit of definition for each section. You may need to include additional rows to capture progress, timeline and budget.

## Requirements
Requirements Tab
Sprint | Requirement Code | Recommendation/Requirement | Change Recommendation | Level of Effort (LOE - Hrs) | Priority | Responsible Party | Comments
Functionality
Month | R1 | Build capability
Month | R2 | Training
Month | R3 | Define SLA
Month | R4 | Reports and Dashboard
Month | R5 | Data migration
Business Process Improvement
Month | R5
Month | R6
Month | R7
Month | R8
Month | R9
Month | R10
Month | R11
Validation
Month | R12 | Security/Privacy
Month | R13 | Testing
Month | R14
Month | R15
Other
Month | R16
Months | R17
0
Keep In Mind | This tab helps determine your MVP and rank requirements to prioritize. Requirement codes can be utilized in communication to keep everyone on the same page. Refer to the Scenario Marketing and Scenario IT tabs to ensure that the latest information is recorded. You can also consider if any other sections, including Business Process Improvement, Validation or other areas are needed. The sections can be customized by project.
Note on A1: This tab highlights each requirement you will be installing, redesigning or building new functionality for. It prioritizes functionality into monthly sprints which you will see are planned into timelines on the 'Project Plan' tab. It's second purpose is to track verification results and record testing activities against Dev, Test and Production.
Note on F2: High - Work Stoppage if not Implemented Medium - Manual work around; Inefficient Low - Nice to have for automation, reduction of steps
Note on G2: Refer to RACI
Note on F4: High - Work Stoppage if not Implemented Medium - Manual work around; Inefficient Low - Nice to have for automation, reduction of steps

## RACI
RACI Tab
Project RACI | [6 empty] | EXAMPLE - Project RACI
Activities | Stakeholder | Change Agent1 | PM/BA | Marketing | Solution Architect | IT | Activities | Stakeholder | Change Agent1 | PM/BA | Marketing | Solution Architect | IT
Definition of Scope | [6 empty] | Definition of Scope | A | S | R | S | S | S
Project Requirements | [6 empty] | Project Requirements | A | S | R | S | S | S
Project Plan | [6 empty] | Project Plan | A | I | R | I | S | I
Project Control | [6 empty] | Project Control | I | I | R | I | S | I
Architecture/Build | [6 empty] | Architecture/Build | A | I | S | I | R | I
Testing (Dev) | [6 empty] | Testing (Dev) | I | I | S | A | R | I
Testing (Functional) | [6 empty] | Testing (Functional) | A | S | S | R | S | S
Deployment | [6 empty] | Deployment | I | I | S | S | R | I
Training | [6 empty] | Training | A | R | I | R | S | R
Post Go-Live Support | [6 empty] | Post Go-Live Support | I | I | I | S | R | I
Responsible | Those that lead the work efforts to achieve the task
Approve | They are accountable for direction and approver
Support | They provide support and effort associated to the activities
Inform | Those that are kept up to date on the project milestones
Company Team: | Project Roles
Business Architect | Project Manager, Business Architect and Business Analysis
Solution Architect | Technical Architect designing, engineering and QAing functionality
Developer | Engineering, developing, coding and unit testing functionality
Stakeholder | Stakeholder, scope management, issues resolutions.
Change Management | Providing Business Process architecture guidance and impact across business areas
Leader | Ensure communication between vendors (company).
IT | Assigned individual within the IT department.
Marketing | Assigned individual within the Marketing department.
Note on A1: This tab highlights roles and responsibilities on the project between the individual team members by project activities. It's helpful to ensure who's accountable for what for collaboratively managing the project.
Note on A3: Add definitions for each activity. Utilize comment function for explanation and example data.
Note on B3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on C3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on D3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on E3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on F3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on G3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on I3: Add definitions for each activity. Utilize comment function for explanation and example data.
Note on J3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on K3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on L3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on M3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on N3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on O3: We encourage you to put in the names of actual stakeholder, architect, etc.
Note on A7: What does Project Control mean? Timeline, Costs, Admin type items
Note on I7: What does Project Control mean? Timeline, Costs, Admin type items
Note on A13: It is suggested to use AB testing as part of Post Go-Live Support
Note on I13: It is suggested to use AB testing as part of Post Go-Live Support
Note on A23: The Business Architect plays a key role in structuring the enterprise in terms of its governance structure, business processes, and business information.
Note on A26: In most cases the CIO or CMO is the primary stakeholder however the GM or other role may be the stakeholder.

## Project_Plan
Project Plan Tab
PHASE 1 |  | MONTH 1 |  |  |  | MONTH 2 |  |  |  | MONTH 3 |  |  |  | MONTH 4 |  |  |  | Open Tasks / Items / Comments
WEEK STARTING
PROJECT ACTIVITIES | STATUS | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
ARCHITECTURE
Set up Project Workbook (Reqs, RACI, Plan, Action Log, Backlog)
Determine collaboration and communication mechanisms
Disovery - Determine Business and Functional Requirements
Baseline Requirements
Set up UAT Environment - where applicable
Identify configuration management approach
Determine Data Approach - Integration/Migration/Management
Determine Business Reporting Needs
BUILD - Dev Environment
Sprint 1 -
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
Activity 6
Push to test/verify/remediate
Sprint 2
Sprint 1 -
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
Activity 6
Push to test/verify/remediate
TESTING - Shared Test Environment
Create Use Cases/Test Scenarios
End to End System Test (Company/Client)
Testing Remediation
Conference Room Pilot
Client Sign-off
DEPLOYMENT
Communication on Go-Live
Production Verification Test
Train the trainer (Sys Admin)
User Training
Production deployment pack
Go-Live (Phase I) - DATE
Client Acceptance
PHASE 2 |  | MONTH 1 |  |  |  | MONTH 2 |  |  |  | MONTH 3 |  |  |  | MONTH 4 |  |  |  | Open Tasks / Items / Comments
WEEK STARTING
PROJECT ACTIVITIES | STATUS | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
ARCHITECTURE
[19 empty] | TIP: | Start discussing/planning phase II scope; key to identify priorities and get started on business process definition in parrellel to deplying PhaseI to keep momentum. New contract and PO for second phase of work.
Note on A1: This tab highlights weekly project activities associated to delivery for architecture, build, test and deployment. All items in black are the responsibility of (company) to drive along with overall engagement and actions to support build. Items in orange we'll need Q and A to support.
Note on B4: Not Started WIP Completed -Status
Note on B49: Not Started WIP Completed -Status

## Test Scenarios - IT
IT Testing Tab
| Scenario Code: | Project Name - Test Case #1
Scenario Title:
Brief Scenario Description:
STEP # | Requirements Code | Process Description | Expected Results | Actual Input | Actual Output | Pass/Fail | Date | By
R1
1
2
3
4
5
6
7
R2
1
2
3
4
5
6
7
R2
1
2
3
4
5
6
7
Note on A1: This log is for the 'tester' to record results of items that don't function as expected based on requirements and design discussions. The appropriate role identified will fix the bugs and mark status of resolution and migration to test.
Note on B7: These codes correlate with the REQUIREMENTS tab R1,R2,R3, etc.

## Action_LOG
Action Log Tab
# | Responsible | Date Assigned | Function | Action Item | Impact | Need By Date | Status | Closure Date | Remarks
A1
A2
A3
A4
A5
A6
A7
A8
A9
A10
A11
Note on A1: This tab highlights very specific tasks needed from team members, with dates, who's it's assigned to and when it's needed by to ensure management of the overall project timelines. It's key to meet delivery of action items by the date defined or go-live date will be delayed.

## Test Scenarios- Marketing
Marketing Testing Tab
| Scenario Code: | Project Name - Test Case #1
Scenario Title:
Brief Scenario Description:
Step # | Requirements Code | Process Description | Expected Results | Actual Input | Actual Output | Pass/Fail | Date | By
RM1
1
2
3
4
5
6
7
RM2
1
2
3
4
5
6
7
RM2
1
2
3
4
5
6
7
Note on A1: This log is for the 'tester' to record results of items that don't function as expected based on requirements and design discussions. The appropriate role identified will fix the bugs and mark status of resolution and migration to test.
Note on B8: These codes correlate with the REQUIREMENTS tab R1,R2,R3, etc.

## Backlog - Post Phase I
Backlog Tab
ID | Identified | Recommendation/Requirement | Change Recommendation | Change Impact | Priority | Level of Effort (LOE - Hrs) | Sprint/Month | Comments
BL1 | New Functionality
BL2 | New Functionality
| Keep in Mind | This tab tracks additional functionality that is out of scope for the project. You may revisit to determine if it should be included now or in the project's second or third phase or if a new project would be required to address this item.

## Training List (hidden)
Start with the overall process from the business perspective: *The process flow in a parred down PPT *Salesforce nomenclatures; Ensure we use the business laungage for training *Then SF hands-on
Sales Leadership Summit in Feb: *How to create an opportunity *How to create a proposal *Case proposal approval process *Case proposal statuses and workflow automation/visibility *Generation of a contract *Adding instruments and generating Conga documents (SPA and Distributor)
Other: Add Solana and Sophia Squs to consolidated case GPO Contracts - Add in to verify workflow approval
Closed/Lost - Why it's important and status? *Forecasting *Reporting *Sales Nurturing
Your reports by role.
"SF Mobile: *Functionality *Adding an account *Logging calls while mobile *Approving "